## Cover
INTEGRATION TEST FOR ENGLISH REVIEW SYSTEM
Project Code | ER
Project Name | English Review System
Target Platform
Release No. | 1
Tester Name | Loc, Vo Thanh
Date Executed | 08 - Apr - 2021
Estimate Duration | 22 hrs
Revision History
Date | Version | Description | Author | Approved
20 - Mar - 2021 | 1.0 | Create Document | Phuong,Dau Tuan
08 - Apr - 2021 | 1.1 | [Server/Backend] Login for Learner | Phuong,Dau Tuan
|  | [Server/Backend] Logout for Learner | Phuong,Dau Tuan
|  | Test [Server/Backend] Register for Learner | Phuong,Dau Tuan
|  | Test[Server/Backend] Create an API to send lesson list data to the client | Phuong,Dau Tuan
|  | Test [Server/Backend] Create an API to send lesson content data to the server | Phuong,Dau Tuan
|  | Test [Server/Backend] Create an API to send practice content data to the client | Phuong,Dau Tuan
|  | Test [Server/Backend] Create an API to send practice according to lesson data to the client | Phuong,Dau Tuan
10 - Apr - 2021 | 1.2 | Test [Frontend] UI for the Login page (Admin) | Loc, Vo Thanh
|  | Test[Frontend] UI for the Login screen (Learner) | Loc, Vo Thanh
|  | Test [Frontend] UI for the Register screen (Learner) | Loc, Vo Thanh
|  | Test[Frontend] UI for the learner profile (Learner) | Loc, Vo Thanh
|  | Test[Frontend] UI for the lesson page (Learner) | Loc, Vo Thanh
|  | Test[Frontend] UI for the practice page (Learner) | Loc, Vo Thanh
13 - Apr - 2021 | 1.3 | Re - test [Server/Backend] Login for Admin | Phuong,Dau Tuan
|  | Re - test [Server/Backend] Logout for Admin | Phuong,Dau Tuan
|  | Re - test [Server/Backend] Login for Learner | Phuong,Dau Tuan
|  | Re - test [Server/Backend] Logout for Learner | Phuong,Dau Tuan
|  | Re - test[Server/Backend] Register for Learner | Phuong,Dau Tuan
|  | Re - test [Server/Backend] Create an API to send lesson list data to the client | Phuong,Dau Tuan
|  | Re - test [Server/Backend] Create an API to send lesson content data to the server | Phuong,Dau Tuan
|  | Re - test [Server/Backend] Create an API to send practice content data to the client | Phuong,Dau Tuan
|  | Re - test [Server/Backend] Create an API to send practice according to lesson data to the client | Phuong,Dau Tuan
|  | Test [Frontend] UI for the Login page (Admin) | Loc, Vo Thanh
|  | Test[Frontend] UI for the Login screen (Learner) | Loc, Vo Thanh
|  | Test [Frontend] UI for the Register screen (Learner) | Loc, Vo Thanh
|  | Test[Frontend] UI for the learner profile (Learner) | Loc, Vo Thanh
|  | Test[Frontend] UI for the lesson page (Learner) | Loc, Vo Thanh
|  | Test[Frontend] UI for the practice page (Learner) | Loc, Vo Thanh

## Test case list
Test case list
Project name |  | ENGLISH REVIEW SYSTEM
Project code |  | Hardware:
- CPU: Intel® Core™ i5
- Ram: 4 GB.
Software:
- Application:
- OS: Windows 10
Test Environment Setup Description |  | Hardware:
- CPU: Intel® Core™ i5
- Ram: 4 GB.
Software:
- OS: Window 10
- Application: Swagger,Visual studio code, Android Device
No | Function name |  | Sheet name | Description | Pre - Condition
1 | [Server/Backend] Login for Learner |  | Login
2 | [Server/Backend] Logout for Learner |  | Logout
3 | [Server/Backend] Register for Learner |  | Register
4 | [Server/Backend] Create an API to send lesson list data to the client |  | View lesson
5 | [Server/Backend] Create an API to send lesson content data to the server |  | Create lesson
6 | [Server/Backend] Create an API to send practice content data to the client |  | View practice
7 | [Server/Backend] Create an API to send practice according to lesson data to the client |  | View question lesson
8 | [Frontend] UI for the Login page (Admin) |  | Login admin
9 | [Frontend] UI for the Login screen (Learner) |  | Login app
10 | [Frontend] UI for the Register screen (Learner) |  | Register FE
11 | [Frontend] UI for the learner profile (Learner) |  | Learner (profile)
12 | [Frontend] UI for the lesson page (Learner) |  | Lesson
13 | [Frontend] UI for the practice page (Learner) |  | Practice

## Login
Module Code | [Server/Backend] Login for Learner
Check Requirement
Tester | Phuong,Dau Tuan
Status | Pass |  |  | Fail |  |  | Not Run |  |  | N/A |  |  | Number of test case
Round test 1 | 3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 3
Round test 2 | 3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 3
Test Case ID | Test case Description | Auth email | Method | Path | Header | Body | Message Expected | Code Expected | Data Expected | Message Actual | Code Actual | Data Actual | Result |  |  | Result |  |  | Note
[13 empty] | Round test 1 |  |  | Round test 2
[13 empty] | Status | Test Date | Tester | Status | Test Date | Tester
TC_01 | learner or admin login |  | POST | /user/login |  | { "username": "dauphuong", "password": "phuong123" } | login | 200 | { "id": "-MZwYnPzQbZv_0Foor_z", "token": "eyJhbGciOiJIUzI1NiIsInR5cCI6IkpXVCJ9.eyJkYXRhIjp7ImF2YXRhciI6Imh0dHBzOi8vZmlyZWJhc2VzdG9yYWdlLmdvb2dsZWFwaXMuY29tL3YwL2IvZXItc3lzdGVtLTJiMzQ2LmFwcHNwb3QuY29tL28vYXZhdGFyLmpwZz9hbHQ9bWVkaWEmdG9rZW49MGViYjU5MmEtNWUxNS00MmQxLThmMGYtMDQ5OTg4NzNkMjUxIiwiY3JlYXRlT25VVEMiOiIyMDIxLTA1LTA1IDEyOjQ0OjQ4IiwiZW1haWwiOiJkYXVwaHVvbmdAZ21haWwuY29tIiwibGFzdExvZ2luIjoiMjAyMS0wNS0zMCAxNTozNjozNCIsInBhc3N3b3JkIjoiJDJiJDEwJGhVNHh2QVYvWEIwSGtaQkdSOUI5TGVHRWZxMHNHT3lZdjlFaHlYeDFBQS5WR2VLdENHNm9TIiwidXNlcm5hbWUiOiJkYXVwaHVvbmciLCJpZCI6Ii1NWndZblB6UWJadl8wRm9vcl96In0sImlhdCI6MTYyMjQzOTA0MiwiZXhwIjoxNjIyNjExODQyfQ.k1YXs0hYF9vfY6QGRtDZZZfoj-4nU_p8KA5bYULaEcw" } | login | 200 | { "id": "-MZwYnPzQbZv_0Foor_z", "token": "eyJhbGciOiJIUzI1NiIsInR5cCI6IkpXVCJ9.eyJkYXRhIjp7ImF2YXRhciI6Imh0dHBzOi8vZmlyZWJhc2VzdG9yYWdlLmdvb2dsZWFwaXMuY29tL3YwL2IvZXItc3lzdGVtLTJiMzQ2LmFwcHNwb3QuY29tL28vYXZhdGFyLmpwZz9hbHQ9bWVkaWEmdG9rZW49MGViYjU5MmEtNWUxNS00MmQxLThmMGYtMDQ5OTg4NzNkMjUxIiwiY3JlYXRlT25VVEMiOiIyMDIxLTA1LTA1IDEyOjQ0OjQ4IiwiZW1haWwiOiJkYXVwaHVvbmdAZ21haWwuY29tIiwibGFzdExvZ2luIjoiMjAyMS0wNS0zMCAxNTozNjozNCIsInBhc3N3b3JkIjoiJDJiJDEwJGhVNHh2QVYvWEIwSGtaQkdSOUI5TGVHRWZxMHNHT3lZdjlFaHlYeDFBQS5WR2VLdENHNm9TIiwidXNlcm5hbWUiOiJkYXVwaHVvbmciLCJpZCI6Ii1NWndZblB6UWJadl8wRm9vcl96In0sImlhdCI6MTYyMjQzOTA0MiwiZXhwIjoxNjIyNjExODQyfQ.k1YXs0hYF9vfY6QGRtDZZZfoj-4nU_p8KA5bYULaEcw" } | Pass | 2021-04-08 | Phuong | Pass | 2021-04-13 | Phuong
TC_02 | login is password wrong |  | POST | /user/login |  | { "username": "dauphuong", "password": "phuong3312" } | login | 200 | password wrong | login | 200 | password wrong | Pass | 2021-04-08 | Phuong | Pass | 2021-04-13 | Phuong
TC_03 | login is username not exists |  | POST | /user/login |  | { "username": "chuaco", "password": "phuong3312" } | login | 200 | username wrong | login | 200 | username wrong | Pass | 2021-04-08 | Phuong | Pass | 2021-04-13 | Phuong

## logout
Module Code | [Server/Backend] Logout for Learner
Check Requirement
Tester | Phuong,Dau Tuan
Status | Pass |  |  | Fail |  |  | Not Run |  |  | N/A |  |  | Number of test case
Round test 1 | 1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1
Round test 2 | 1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1
Test Case ID | Test case Description | Auth email | Method | Path | Header | Body | Message Expected | Code Expected | Data Expected | Message Actual | Code Actual | Data Actual | Result |  |  | Result |  |  | Note
[13 empty] | Round test 1 |  |  | Round test 2
[13 empty] | Status | Test Date | Tester | Status | Test Date | Tester
TC_01 | Logout after login |  | POST | /user/logout | Accept: application/json Authorization: Bearer {{ACCESS_TOKEN}} | { "id": "-MZwYnPzQbZv_0Foor_z" } | Request handled successfully | 200 | { "message": "Logout Success" } | Request handled successfully | 200 | { "message": "Logout Success" } | Pass | 2021-04-08 | Phuong | Pass | 2021-04-13 | Phuong

## Register
Module Code | [Server/Backend] Register for Learner
Check Requirement
Tester | Phuong,Dau Tuan
Status | Pass |  |  | Fail |  |  | Not Run |  |  | N/A |  |  | Number of test case
Round test 1 | 3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 3
Round test 2 | 3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 3
Test Case ID | Test case Description | Auth email | Method | Path | Header | Body | Message Expected | Code Expected | Data Expected | Message Actual | Code Actual | Data Actual | Result |  |  | Result |  |  | Note
[13 empty] | Round test 1 |  |  | Round test 2
[13 empty] | Status | Test Date | Tester | Status | Test Date | Tester
TC_01 | Learners can register an account to join the application success |  | POST | /user/register |  | { "username": "dauphuong123", "password": "phuong123", "email": "dauphuong@gmail.com" } | The account was successfully created | 200 | Successlly | The account was successfully created | 200 | Successlly | Pass | 2021-04-08 | Phuong | Pass | 2021-04-13 | Phuong
TC_02 | Register learner with information empty |  | POST | /user/register |  | { "username": "", "password": "", "email": "" } | Error: Bad Request | 400 | { "errors": [ { "value": "", "msg": "username does not Empty", "param": "username", "location": "body" } ] } | Error: Bad Request. | 400 | { "errors": [ { "value": "", "msg": "username does not Empty", "param": "username", "location": "body" } ] } | Pass | 2021-04-08 | Phuong | Pass | 2021-04-14 | Phuong
TC_03 | Learner can not register brand information with username already exists |  | POST | /user/register |  | { "username": "dauphuong123", "password": "phuong123", "email": "dauphuong@gmail.com" } | The account was successfully created | 200 | Account already exists | The account was successfully created | 200 | Account already exists | Pass | 2021-04-08 | Phuong | Pass | 2021-04-15 | Phuong

## View lesson
Module Code | [Server/Backend] Create an API to send lesson list data to the client
Check Requirement
Tester | Phuong,Dau Tuan
Status | Pass |  |  | Fail |  |  | Not Run |  |  | N/A |  |  | Number of test case
Round test 1 | 3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 3
Round test 2 | 3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 3
Test Case ID | Test case Description | Auth email | Method | Path | Header | Body | Message Expected | Code Expected | Data Expected | Message Actual | Code Actual | Data Actual | Result |  |  | Result |  |  | Note
[13 empty] | Round test 1 |  |  | Round test 2
[13 empty] | Status | Test Date | Tester | Status | Test Date | Tester
TC_01 | Allow show all lesson |  | GET | /lesson/findAll | Authorization: Bearer {{ACCESS_TOKEN}} |  | The list of the lesson | 200 | [ { "content": "Động từ là từ chỉ hành động hoặc trạng thái của chủ ngữ. Mọi câu đều phải có động từ....", "createOnUTC": "2021-05-29 10:46:57", "idTopic": "-Marif-OqX8e4iZMKuVF", "title": "Verb(động từ)", "id": "-MariyxxEq_w7rucgCfv", "nameTopic": "Verb (động từ)" }, ... ] | The list of the lesson | 200 | [ { "content": "Động từ là từ chỉ hành động hoặc trạng thái của chủ ngữ. Mọi câu đều phải có động từ....", "createOnUTC": "2021-05-29 10:46:57", "idTopic": "-Marif-OqX8e4iZMKuVF", "title": "Verb(động từ)", "id": "-MariyxxEq_w7rucgCfv", "nameTopic": "Verb (động từ)" }, ... ] | Pass | 2021-04-08 | Phuong | Pass | 2021-04-13 | Phuong
TC_02 | Allows displaying the lessons by id |  | GET | ​/lesson​/findById​/-MarkdU02l71oLNAyqRM | Authorization: Bearer {{ACCESS_TOKEN}} |  | The lesson description by id | 200 | [ { "content": "Chủ ngữ là chủ thể của hành động trong câu, thường đứng trước động từ (verb). Chủ ngữ thường là một danh từ (noun) hoặc một ngữ danh từ (noun phrase - một nhóm từ kết thúc bằng một danh từ, trong trường hợp này ngữ danh ...", "createOnUTC": "2021-05-29 10:54:13", "idTopic": "-MarjtxRIxQB7CGIxPMH", "title": "Subject(chủ ngữ)", "id": "-MarkdU02l71oLNAyqRM" } ] | The lesson description by id | 200 | [ { "content": "Chủ ngữ là chủ thể của hành động trong câu, thường đứng trước động từ (verb). Chủ ngữ thường là một danh từ (noun) hoặc một ngữ danh từ (noun phrase - một nhóm từ kết thúc bằng một danh từ, trong trường hợp này ngữ danh ...", "createOnUTC": "2021-05-29 10:54:13", "idTopic": "-MarjtxRIxQB7CGIxPMH", "title": "Subject(chủ ngữ)", "id": "-MarkdU02l71oLNAyqRM" } ] | Pass | 2021-04-09 | Phuong | Pass | 2021-04-14 | Phuong
TC_03 | Allows displaying the list of lessons by topic |  | GET | ​/lesson​/findById​/-Marik05XIp7-rcKmQSv | Authorization: Bearer {{ACCESS_TOKEN}} |  | The lesson description by topic | 200 | [ { "content": "Vị ngữ là&nbsp;từ&nbsp;hoặc cụm từ&nbsp;chỉ đối tượng tác động của chủ ngữ. .....", "createOnUTC": "2021-05-29 10:47:38", "idTopic": "-Marik05XIp7-rcKmQSv", "title": "Complement (vị ngữ)", "id": "-Marj7yk9Tl2rxUH2IGz" } ... ] | The lesson description by topic | 200 | [ { "content": "Vị ngữ là&nbsp;từ&nbsp;hoặc cụm từ&nbsp;chỉ đối tượng tác động của chủ ngữ. .....", "createOnUTC": "2021-05-29 10:47:38", "idTopic": "-Marik05XIp7-rcKmQSv", "title": "Complement (vị ngữ)", "id": "-Marj7yk9Tl2rxUH2IGz" } ... ] | Pass | 2021-04-09 | Phuong | Pass | 2021-04-14 | Phuong

## Create lesson
Module Code | [Server/Backend] Create an API to send lesson content data to the server
Check Requirement
Tester | Phuong,Dau Tuan
Status | Pass |  |  | Fail |  |  | Not Run |  |  | N/A |  |  | Number of test case
Round test 1 | 2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 2
Round test 2 | 2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 2
Test Case ID | Test case Description | Auth email | Method | Path | Header | Body | Message Expected | Code Expected | Data Expected | Message Actual | Code Actual | Data Actual | Result |  |  | Result |  |  | Note
[13 empty] | Round test 1 |  |  | Round test 2
[13 empty] | Status | Test Date | Tester | Status | Test Date | Tester
TC_01 | Admin can create lessons |  | POST | lesson/save | Authorization: Bearer {{ACCESS_TOKEN}} Accept: application/json Content-Type: application/json | { "title": "Động từ cơ bản", "content": "Động từ là từ chỉ hành động hoặc trạng thái của chủ ngữ …….", "idTopic": "-MZwnB80pewmPasdGSXI" } | The Lesson was successfully created | 200 | successful | The Lesson was successfully created | 200 | successful | Pass | 2021-04-08 | Phuong | Pass | 2021-04-13 | Phuong
TC_02 | admin cannot create lessons with empty information |  | POST | lesson/save | Authorization: Bearer {{ACCESS_TOKEN}} Accept: application/json Content-Type: application/json | { "title": "", "content": "", "idTopic": "" } | Error: Bad Request | 400 | { "errors": [ { "value": "", "msg": "topic does not Empty", "param": "idTopic", "location": "body" }, { "value": "", "msg": "content does not Empty", "param": "content", "location": "body" }, { "value": "", "msg": "title does not Empty", "param": "title", "location": "body" } ] } | Error: Bad Request | 400 | { "errors": [ { "value": "", "msg": "topic does not Empty", "param": "idTopic", "location": "body" }, { "value": "", "msg": "content does not Empty", "param": "content", "location": "body" }, { "value": "", "msg": "title does not Empty", "param": "title", "location": "body" } ] } | Pass | 2021-04-09 | Phuong | Pass | 2021-04-14 | Phuong

## view question lesson
Module Code | [Server/Backend] Create an API to send practice according to lesson data to the client
Check Requirement
Tester | Diem, Pham Thi Thuy
Status | Pass |  |  | Fail |  |  | Not Run |  |  | N/A |  |  | Number of test case
Round test 1 | 1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1
Round test 2 | 1 |  |  | 0 |  |  | 0 |  |  | 0
Test Case ID | Test case Description | Auth email | Method | Path | Header | Body | Message Expected | Code Expected | Data Expected | Message Actual | Code Actual | Data Actual | Result |  |  | Result |  |  | Note
[13 empty] | Round test 1 |  |  | Round test 2
[13 empty] | Status | Test Date | Tester | Status | Test Date | Tester
TC_01 | Allows displaying the question by idExam |  | GET | ​/question​/findAllByIdLesson​/-MarkdU02l71oLNAyqRM | Authorization: Bearer {{ACCESS_TOKEN}} |  | The questions description by lesson | 200 | [ { "idLesson": "-MarkdU02l71oLNAyqRM", "idQuestion": "-MZwqkWiE91dagP-UQdU", "id": "-Mavqc2lz-2SfKuqpuzD" }, { "idLesson": "-MarkdU02l71oLNAyqRM", "idQuestion": "-Mak0jFPfHe27xOlOfvI", "id": "-Mavqc2moPxQT94toHBh" }, { "idLesson": "-MarkdU02l71oLNAyqRM", "idQuestion": "-ManBMLmXf-t6pmdSSEx", "id": "-Mavqc2n5saQuQt8GPZp" }, .... ] | The questions description by lesson | 200 | [ { "idLesson": "-MarkdU02l71oLNAyqRM", "idQuestion": "-MZwqkWiE91dagP-UQdU", "id": "-Mavqc2lz-2SfKuqpuzD" }, { "idLesson": "-MarkdU02l71oLNAyqRM", "idQuestion": "-Mak0jFPfHe27xOlOfvI", "id": "-Mavqc2moPxQT94toHBh" }, { "idLesson": "-MarkdU02l71oLNAyqRM", "idQuestion": "-ManBMLmXf-t6pmdSSEx", "id": "-Mavqc2n5saQuQt8GPZp" }, .... ] | Pass | 2021-04-09 | Phuong | Pass | 2021-04-14 | Phuong

## View practice
Module Code | [Server/Backend] Create an API to send practice content data to the client
Check Requirement
Tester | Phuong, Dau Tuan
Status | Pass |  |  | Fail |  |  | Not Run |  |  | N/A |  |  | Number of test case
Round test 1 | 3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 3
Round test 2 | 3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 3
Test Case ID | Test case Description | Auth email | Method | Path | Header | Body | Message Expected | Code Expected | Data Expected | Message Actual | Code Actual | Data Actual | Result |  |  | Result |  |  | Note
[13 empty] | Round test 1 |  |  | Round test 2
[13 empty] | Status | Test Date | Tester | Status | Test Date | Tester
TC_01 | Allow show all practice | manager_4@gmail.com | POST | ​/exam​/findByType​/practice | Authorization: Bearer {{ACCESS_TOKEN}} |  | The questions description by type | 200 | [ { "createOnUTC": "2021-05-28 15:15:37", "timeSet": "3000", "title": "Cuộc thi dịch", "type": "practice", "id": "-ManXsavJIEF9WsQA024" }, { "createOnUTC": "2021-05-29 13:02:26", "timeSet": "50000", "title": "Cuộc thi Đà Nẵng", "type": "practice", "id": "-MasCzSd2BYxs9qtcf_M" },..... ] | The questions description by type | 200 | [ { "createOnUTC": "2021-05-28 15:15:37", "timeSet": "3000", "title": "Cuộc thi dịch", "type": "practice", "id": "-ManXsavJIEF9WsQA024" }, { "createOnUTC": "2021-05-29 13:02:26", "timeSet": "50000", "title": "Cuộc thi Đà Nẵng", "type": "practice", "id": "-MasCzSd2BYxs9qtcf_M" },..... ] | Pass | 2021-04-08 | Phuong | Pass | 2021-04-13 | Phuong
TC_02 | Allows displaying the practice by id |  | GET | ​/exam​/findById​/-MavkNd1g2QWnf68gtJQ | Authorization: Bearer {{ACCESS_TOKEN}} |  | The exam description by id | 200 | [ { "createOnUTC": "2021-05-30 05:31:33", "timeSet": "5000", "title": "Cuộc thi học sinh giỏi", "type": "practice", "id": "-MavkNd1g2QWnf68gtJQ" } ] | The exam description by id | 200 | [ { "createOnUTC": "2021-05-30 05:31:33", "timeSet": "5000", "title": "Cuộc thi học sinh giỏi", "type": "practice", "id": "-MavkNd1g2QWnf68gtJQ" } ] | Pass | 2021-04-09 | Phuong | Pass | 2021-04-14 | Phuong
TC_03 | Allows displaying the question by idExam |  | GET | ​/question​/findAllByIdExam​/-MasVObo1JhzEhJkkWUD | Authorization: Bearer {{ACCESS_TOKEN}} |  | The questions description by id | 200 | [ { "idExam": "-MasVObo1JhzEhJkkWUD", "idQuestion": "-MZwqkWiE91dagP-UQdU", "id": "-MasVOgKeVnSxF7IYzFM" }, { "idExam": "-MasVObo1JhzEhJkkWUD", "idQuestion": "-Mak0jFPfHe27xOlOfvI", "id": "-MasVOgOskTGWneJ04uy" }, …… ] | The questions description by id | 200 | [ { "idExam": "-MasVObo1JhzEhJkkWUD", "idQuestion": "-MZwqkWiE91dagP-UQdU", "id": "-MasVOgKeVnSxF7IYzFM" }, { "idExam": "-MasVObo1JhzEhJkkWUD", "idQuestion": "-Mak0jFPfHe27xOlOfvI", "id": "-MasVOgOskTGWneJ04uy" }, …… ] | Pass | 2021-04-09 | Phuong | Pass | 2021-04-14 | Phuong

## create practice
Module Code | [Server/Backend] Create an API to send practice according to lesson data to the client
Check Requirement
Tester | Diem, Pham Thi Thuy
Status | Pass |  |  | Fail |  |  | Not Run |  |  | N/A |  |  | Number of test case
Round test 1 | 3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 3
Round test 2 | 3 |  |  | 0 |  |  | 0 |  |  | 0
Test Case ID | Test case Description | Auth email | Method | Path | Header | Body | Message Expected | Code Expected | Data Expected | Message Actual | Code Actual | Data Actual | Result |  |  | Result |  |  | Note
[13 empty] | Round test 1 |  |  | Round test 2
[13 empty] | Status | Test Date | Tester | Status | Test Date | Tester
TC_01 | Admin can create practice |  | POST | exam/save | Authorization: Bearer {{ACCESS_TOKEN}} Accept: application/json Content-Type: application/json | { "title": "Đề thực hành động từ", "type": "practice", "listQuestion": [ "-ManBMLr50wBC68PcQLx", "-Mar5hH7wVug12sVnNiC", "-Mar5hHESyGXYVPiagUs" ], "timeSet": "900000" } | The Exam was successfully created | 200 | successful | The Exam was successfully created | 200 | successful | Pass | 2021-04-08 | Phuong | Pass | 2021-04-13 | Phuong
TC_02 | admin cannot create practice with empty information |  | POST | lesson/save | Authorization: Bearer {{ACCESS_TOKEN}} Accept: application/json Content-Type: application/json | { "title": "", "type": "", "timeSet": "" } | Error: Bad Request | 400 | { "errors": [ { "value": "", "msg": "Invalid type", "param": "type", "location": "body" }, { "value": "", "msg": "time set does not Empty", "param": "timeSet", "location": "body" }, { "value": "", "msg": "title does not Empty", "param": "title", "location": "body" } ] } | Error: Bad Request | 400 | { "errors": [ { "value": "", "msg": "Invalid type", "param": "type", "location": "body" }, { "value": "", "msg": "time set does not Empty", "param": "timeSet", "location": "body" }, { "value": "", "msg": "title does not Empty", "param": "title", "location": "body" } ] } | Pass | 2021-04-09 | Phuong | Pass | 2021-04-14 | Phuong
TC_03 | Admin can create practice with listQuestion without |  | POST | lesson/save | Authorization: Bearer {{ACCESS_TOKEN}} Accept: application/json Content-Type: application/json | { "title": "Đề thực hành động từ", "type": "practice", "timeSet": "900000" } | The Exam was successfully created | 200 | successful | The Exam was successfully created | 200 | successful | Pass | 2021-04-09 | Phuong | Pass | 2021-04-14 | Phuong

## Login admin
Module Code | [Frontend] Test UI for login admin
Check Requirement
Tester
Status | Pass | Fail |  | Not Run | N/A |  | Number of test case
Round test 1 | 5 | 0 |  | 0 | 0 |  | 5
Round test 2 | 5 | 0 |  | 0 | 0 |  | 5
Test Case ID | Test case Description | Pre-condition | Step | Excepted Output | Actual Output | Result |  |  | Result |  |  | Note
[6 empty] | Round test 1 |  |  | Round test 2
[6 empty] | Status | Test Date | Tester | Status | Test Date | Tester
GUI Testing
TC_01 | [UserName] textbox |  |  | Alignment=middle, under [Sign in] label | Alignment=middle,under [Sign in to start your session] label | Pass | 10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | Enabled | Enabled
TC_02 | [Password] textbox |  |  | Alignment=middle, under [Email] textbox | Alignment=middle,under [Email] textbox | Pass | 10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | Enabled | Enabled
TC_03 | [Sign In] button |  |  | Alignment=right, under [Password] textbox | Alignment=left,under [Password] textbox | Pass | 10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | type=“button” | type=“button”
Functional Testing
TC_01 | Verify user can login with valid information | Connect to internet | Step 1: Navigate to the URL: http://localhost:3000/admin/login Step 2: Login with valid user name and password Step 3: Click Login in button | 1. Dashboard page display | 1. Dashboard page display | Pass | 10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
TC_02 | Verify display error message when login with invalid data | Connect to internet | Step 1: Navigate to the URL:http://localhost:3000/admin/login Step 2: Login with invalid user name and password Step 3: Click Login in button | 1. Dashboard page not display 2. Display error message | 1. Dashboard page not display 2. Display error message | Pass | 10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc

## Login app
Module Code | Login learner
Check Requirement
Tester
Status | Pass | Fail |  | Not Run | N/A |  | Number of test case
Round test 1 | 6 | 0 |  | 0 | 0 |  | 6
Round test 2 | 6 | 0 |  | 0 | 0 |  | 6
Test Case ID | Test case Description | Pre-condition | Step | Excepted Output | Actual Output | Result |  |  | Result |  |  | Note
[6 empty] | Round test 1 |  |  | Round test 2
[6 empty] | Status | Test Date | Tester | Status | Test Date | Tester
GUI Testing
TC_01 | [Tên tài khoản] textbox |  |  | Alignment=middle, under [Sign in to start your session] label | Alignment=middle,under [Đăng Nhập] label | Pass | 10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | Enabled | Enabled
TC_02 | [Mật khẩu] textbox |  |  | Alignment=middle, under [UserName] textbox | Alignment=middle,under [UserName] textbox | Pass | 10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | Enabled | Enabled
TC_03 | [Đăng Nhập] button |  |  | Alignment=right, under [Password] textbox | Alignment=left,under [Password] textbox | Pass | 10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | type=“button” | type=“button”
Functional Testing
TC_04 | Verify user can login with valid information | Connect to internet | Step 1: Navigate to the login Screen Step 2: Login with valid user name and password Step 3: Click [Đăng Nhập] button | 1. Display message "Bạn đã đăng nhập thành công" 2. Home screen display | 1. Display message "Bạn đã đăng nhập thành công" 2. Home screen display | Pass | 10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
TC_05 | Verify display error message when login with invalid data | Connect to internet | Step 1: Navigate to the login Screen Step 2: Login with invalid user name and password Step 3: Click [Đăng Nhập] button | 1. Display message "Tài Khoản/ Mật khẩu không đúng" 2. Home screen display | 1. Display message "Tài Khoản/ Mật khẩu không đúng" 2. Home screen display | Pass | 10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
TC_06 | Verify error message displayed on login with no data input | Connect to internet | Step 1: Navigate to the login Screen Step 2: Login has no valid user name and password Step 3: Click [Đăng Nhập] button | 1. Display message "Tài Khoản/ Mật khẩu không đúng" 2. Home screen display | 1. Display message "Tài Khoản/ Mật khẩu không đúng" 2. Home screen display | Pass | 10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc

## Learner (profile)
Module Code | Profile learner
Check Requirement
Tester
Status | Pass | Fail |  | Not Run | N/A |  | Number of test case
Round test 1 | 6 | 0 |  | 0 | 0 |  | 6
Round test 2 | 5 | 0 |  | 0 | 0 |  | 5
Test Case ID | Test case Description | Pre-condition | Step | Excepted Output | Actual Output | Result |  |  | Result |  |  | Note
[6 empty] | Round test 1 |  |  | Round test 2
[6 empty] | Status | Test Date | Tester | Status | Test Date | Tester
GUI Testing
TC_01 | [Avatar] image |  |  | Alignment=center, | Alignment=center, | Pass | 10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | Type="image" | Type="image"
TC_02 | [Tên Đăng Nhập] textbox |  |  | Alignment=center, under [Avatar] image | Alignment=middle,under [Avatar] image | Pass | 10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | Type="textbox" | Type="textbox"
TC_03 | [Email] button |  |  | Alignment=center, under [UserName] image | Alignment=center, under [UserName] image | Pass | 10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | Type="textbox" | Type="textbox"
TC_04 | [Đổi mật khẩu] button |  |  | Alignment=center, under [Email] button | Alignment=center, under [Email] button | Pass | 10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | Type="button" | Type="button"
TC_05 | [Đăng Xuất] button |  |  | Alignment=center, under [Đổi mật khẩu] button | Alignment=center, under [Đổi mật khẩu] button | Pass | 10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | Type="button" | Type="button"
Functional Testing
TC_06 | Change the password | Internet Connection | 1. Login successfully 2. Click[Profile] button 3. Click[Đổi Mật khẩu button] | Change the password successfully | Change the password failed | Not run | '10 - Apr - 2021 | Loc | Not run | 31 - May - 2021 | Loc
TC_07 | Change the email | Internet Connection | 1. Login successfully 2. Click[Profile] button 3. Click[Email] | Change the email successfully | Change the email failed | Not run | '10 - Apr - 2021 | Loc | Not run | '31 - May - 2021 | Loc
TC_08 | Logout | Internet Connection | 1. Login successfully 2. Click[Profile] button 3. Click[Đăng Xuất] | Display login screen | Display login screen | Pass | '10 - Apr - 2021 | Loc | Not run | '31 - May - 2021 | Loc
TC_09 | Change the avatar | Internet Connection | 1. Login successfully 2. Click[Profile] button 3. Click[Avatar] image | Change the avatar successfully | Change the avatar failer | Not run | '10 - Apr - 2021 | Loc | Not run | '31 - May - 2021 | Loc

## Lesson
Module Code | [Frontend] Lesson
Check Requirement
Tester
Status | Pass | Fail |  | Not Run | N/A |  | Number of test case
Round test 1 | 21 | 2 |  | 0 | 0 |  | 23
Round test 2 | 23 | 0 |  | 0 | 0 |  | 23
Test Case ID | Test case Description | Pre-condition | Step | Excepted Output | Actual Output | Result |  |  | Result |  |  | Note
[6 empty] | Round test 1 |  |  | Round test 2
[6 empty] | Status | Test Date | Tester | Status | Test Date | Tester
GUI Testing
TC_01 | [Bắt đầu học] button |  |  | Alignment=middle, under [Chúng ta bắt đầu nào] label | Alignment=middle, under [Chúng ta bắt đầu nào] label | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | type="button" | type="button"
TC_02 | [List topic] button |  |  | Alignment=middle | Alignment=middle | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | type="button" | type="button"
TC_03 | [List lesson] button |  |  | Alignment=middle | Alignment=middle | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | type="button" | type="button"
TC_04 | [Lesson content] textbox |  |  | Alignment=middle | Alignment=middle | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | type="textbox" | type="textbox"
TC_05 | [Làm bài tập] button |  |  | Alignment=middle, under [Lesson content] textbox | Alignment=middle, under [Lesson content] textbox | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | type="button" | type="button"
TC_06 | [Question content] textbox |  |  | Alignment=middle, after click [Làm bài tập] button | Alignment=middle, after click [Làm bài tập] button | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | type="textbox" | type="textbox"
TC_07 | [Answer Choose] radiobutton |  |  | Alignment=left, under [Report button] | Alignment=left, under [Report button] | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | type="radiobutton" | type="radiobutton"
TC_08 | [Report] button |  |  | Alignment=left, above [Answer Choose] radiobutton | Alignment=left, above [Answer Choose] radiobutton | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | type="button" | type="button"
TC_09 | [Nộp bài] button |  |  | Alignment=center, under[Question content] textbox | Alignment=center, under[Question content] textbox | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | type="button" | type="button"
TC_10 | [Result] textbox |  |  | Alignment=center | Alignment=center | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | type="textbox" | type="textbox"
TC_11 | [Kết thúc] button |  |  | Alignment=right, under[Result] button | Alignment=right, under[Result] button | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | type="button" | type="button"
TC_12 | [Xem đáp án/ Làm lại]button |  |  | Alignment=right, under[Kết thúc] button | Alignment=right, under[Kết thúc] button | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | type="button" | type="button"
Functional Testing
TC_13 | Show list topic | Connect to internet and navigate to the Try on screen | 1. Successful logining in Home page 2. Click[Bắt đầu học] button | Display topic screen | Display topic screen | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
TC_14 | Show list lesson of the topic | Connect to internet and navigate to the Try on screen | 1. Successful logining in Home page 2. Click[Bắt đầu học] button 3. Click [Topic] button | Display lesson screen | Display lesson screen | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
TC_15 | Show lesson content | Connect to internet and navigate to the Try on screen | 1. Successful logining in Home page 2. Click[Bắt đầu học] button 3. Click [Topic] button 4. Click [Lesson] button | Display lesson content screen | Display lesson content screen | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
TC_16 | Show practice by the lesson | Connect to internet and navigate to the Try on screen | 1. Successful logining in Home page 2. Click[Bắt đầu học] button 3. Click [Topic] button 4. Click [Lesson] button 5. Click [Làm bài tập] button | Display content of practice according to the lesson | Display content of practice according to the lesson | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
TC_17 | Select on the answers on the question texbox | Connect to internet and navigate to the Try on screen | 1. Successful logining in Home page 2. Click[Bắt đầu học] button 3. Click [Topic] button 4. Click [Lesson] button 5. Click [Làm bài tập] button | After choosing, a blue tick will appear on the selected answer | After choosing, a blue tick will appear on the selected answer | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
TC_18 | Click the [Nộp bài] button to see the score |  | 1. Successful logining in Home page 2. Click[Bắt đầu học] button 3. Click [Topic] button 4. Click [Lesson] button 5. Click [Làm bài tập] button 6. Selcect all answer | Display the number of points achieved | Display the number of points achieved | Fail | '10 - Apr - 2021 | Loc | Pass | 31 - May - 2021 | Loc
TC_19 | Click the [Kết thúc] button to navigate home screen |  | 1. Successful logining in Home page 2. Click[Bắt đầu học] button 3. Click [Topic] button 4. Click [Lesson] button 5. Click [Làm bài tập] button 6. Selcect all answer 7. Click [Nộp bài] button | Display home screen | Display home screen | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
TC_20 | Click the [Xem đáp án] button to see the answers to the questions |  | 1. Successful logining in Home page 2. Click[Bắt đầu học] button 3. Click [Topic] button 4. Click [Lesson] button 5. Click [Làm bài tập] button 6. Selcect all answer 7. Click [Nộp bài] button | Display result screen | Display result screen | Fail | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
TC_21 | Click [Report] button |  | 1. Successful logining in Home page 2. Click[Bắt đầu học] button 3. Click [Topic] button 4. Click [Lesson] button 5. Click [Làm bài tập] button | Display report screen | Display report screen | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
TC_22 | Enter the content you want to report into textinput |  | 1. Successful logining in Home page 2. Click[Bắt đầu học] button 3. Click [Topic] button 4. Click [Lesson] button 5. Click [Làm bài tập] button 6. Click on [Report] button 7. Click on [Submit] button | The report content of the question is sent to the system admin | The report content of the question is sent to the system admin | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
TC_23 | Click[Cancel]button |  | 1. Successful logining in Home page 2. Click[Bắt đầu học] button 3. Click [Topic] button 4. Click [Lesson] button 5. Click [Làm bài tập] button 6. Click on [Report] button 7. Click on [Cancel] button | Go back exam content screen | Go back exam content screen | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc

## Practice
Module Code | List of the practice
Check Requirement
Tester | Han, Hoang Gia Bao
Status | Pass | Fail |  | Not Run | N/A |  | Number of test case
Round test 1 | 16 | 1 |  | 0 | 0 |  | 17
Round test 2 | 17 | 0 |  | 0 | 0 |  | 17
Test Case ID | Test case Description | Pre-condition | Step | Excepted Output | Actual Output | Result |  |  | Result |  |  | Note
[6 empty] | Round test 1 |  |  | Round test 2
[6 empty] | Status | Test Date | Tester | Status | Test Date | Tester
GUI Testing
TC_01 | [Luyện tập] button |  |  | Alignment=center, under [Chúng ta bắt đầu nào] label | Alignment=center, under [Chúng ta bắt đầu nào] label | Pass | 2021-05-30 | Loc | Pass | 2021-06-01 | Loc
|  |  |  | Type= "button" | Type= "button"
TC_02 | [Practice list] button |  |  | Alignment=center , center of screen | Alignment=center , center of screen | Pass | 2021-05-30 | Loc | Pass | 2021-06-01 | Loc
|  |  |  | Type= "button" | Type= "button"
TC_03 | [Practice content] textbox | Access Practice screen and press [Practice] button |  | Alignment=center | Alignment=center | Pass | 2021-05-30 | Loc | Pass | 2021-06-01 | Loc
|  |  |  | Type= "textbox" | Type= "textbox"
TC_04 | [Question content] textbox |  |  | Alignment=middle, after click [Làm bài tập] button | Alignment=middle, after click [Làm bài tập] button | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | type="textbox" | type="textbox"
TC_05 | [Answer Choose] radiobutton |  |  | Alignment=left, under [Report button] | Alignment=left, under [Report button] | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | type="radiobutton" | type="radiobutton"
TC_06 | [Report] button |  |  | Alignment=left, above [Answer Choose] radiobutton | Alignment=left, above [Answer Choose] radiobutton | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | type="button" | type="button"
TC_07 | [Nộp bài] button |  |  | Alignment=center, under[Question content] textbox | Alignment=center, under[Question content] textbox | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | type="button" | type="button"
TC_08 | [Result] textbox |  |  | Alignment=center | Alignment=center | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | type="textbox" | type="textbox"
TC_09 | [Kết thúc] button |  |  | Alignment=right, under[Result] button | Alignment=right, under[Result] button | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | type="button" | type="button"
TC_10 | [Xem đáp án/ Làm lại]button |  |  | Alignment=right, under[Kết thúc] button | Alignment=right, under[Kết thúc] button | Pass | 10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | type="button" | type="button"
Functional Testing
TC_11 | Select on the answers on the question texbox |  | 1. Successful logining in Home page 2. Click on [Luyện tập] button 3. Click on [Practice list] button | After choosing, a blue tick will appear on the selected answer | After choosing, a blue tick will appear on the selected answer | Pass | 2021-05-30 | Loc | Pass | 31/05/20211 | Loc
TC_12 | Click the [Nộp bài] button to see the score |  | 1. Successful logining in Home page 2. Click on [Luyện tập] button 3. Click on [Practice list] button 4. Select all answer | Display the number of points achieved | Display the number of points achieved | Fail | 2021-05-30 | Loc | Pass | 31/05/20211 | Loc
TC_13 | Click the [Kết thúc] button to navigate home screen |  | 1. Successful logining in Home page 2. Click on [Luyện tập] button 3. Click on [Practice list] button 4. Select all answer 5. Click [Nộp bài]button | Display home screen | Display home screen | Pass | 2021-05-30 | Loc | Pass | 31/05/20211 | Loc
TC_14 | Click the [Xem đáp án] button to see the answers to the questions |  | 1. Successful logining in Home page 2. Click on [Luyện tập] button 3. Click on [Practice list] button 4. Select all answer 5. Click [Nộp bài]button | Display result screen | Display result screen | Pass | 2021-05-30 | Loc | Pass | 31/05/20211 | Loc
TC_04 | Click [Report] button |  | 1. Successful logining in Home page 2. Click on [Luyện tập] button 3. Click on [Practice list] button | Display report screen | Display report screen | Pass | 2021-05-30 | Loc | Pass | 31/05/20211 | Loc
TC_05 | Enter the content you want to report into textinput |  | 1. Successful logining in Home page 2. Click on [Luyện tập] button 3. Click on [Practice list] button 4. Click on [Report] button 5. Click on [Submit] button | The report content of the question is sent to the system admin | The report content of the question is sent to the system admin | Pass | 2021-05-30 | Loc | Pass | 31/05/20211 | Loc
TC_06 | Click[Cancel]button |  | 1. Successful logining in Home page 2. Click on [Luyện tập] button 3. Click on [Practice list] button 4. Click on [Report] button | Go back exam content screen | Go back exam content screen | Pass | 2021-05-30 | Loc | Pass | 31/05/20211 | Loc

## Register FE
Module Code | Register
Check Requirement
Tester
Status | Pass | Fail |  | Not Run | N/A |  | Number of test case
Round test 1 | 7 | 0 |  | 0 | 0 |  | 7
Round test 2 | 7 | 0 |  | 0 | 0 |  | 7
Test Case ID | Test case Description | Pre-condition | Step | Excepted Output | Actual Output | Result |  |  | Result |  |  | Note
[6 empty] | Round test 1 |  |  | Round test 2
[6 empty] | Status | Test Date | Tester | Status | Test Date | Tester
GUI Testing
TC_01 | [Tên tài khoản] textbox |  |  | Alignment=middle, under [Đăng ký] label | Alignment=middle, under [Đăng ký] label | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | Type="textbox" | Type="textbox"
TC_02 | [Password] textbox |  |  | Alignment=middle, under [Tên tài khoản] textbox | Alignment=middle, under [Tên tài khoản] textbox | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | Type="textbox" | Type="textbox"
TC_03 | [Email] textbox |  |  | Alignment=middle, under [Password] textbox | Alignment=middle, under [Password] textbox | Pass | '10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | Type="textbox" | Type="textbox"
TC_04 | [Đăng Ký] button |  |  | Alignment=middle, under [Email] textbox | Alignment=middle, under [Email] textbox | Pass | 10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
|  |  |  | Type="button" | Type="button"
Functional Testing
TC_05 | Verify user can login with valid information | Connect to internet | Step 1: Navigate to the login Screen Step 2: Click [Tạo tài khoản] button Step 3: Register with valid user name, password and email Step 4: Click [Đăng ký] button | 1. Display message "Bạn đã đăng ký thành công" 2. Login screen display | 1. Display message "Bạn đã đăng ký thành công" 2. Login screen display | Pass | 10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
TC_06 | Verify error message displayed on register with no data input | Connect to internet | Step 1: Navigate to the login Screen Step 2: Click [Tạo tài khoản] button Step 3: Register with valid user name, password and email Step 4: Click [Đăng ký] button | 1. Display message "Vui lòng điền đầy đủ thông tin". | 1. Display message "Vui lòng điền đầy đủ thông tin". | Pass | 10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc
TC_07 | Verify display error message when login with invalid data | Connect to internet | Step 1: Navigate to the login Screen Step 2: Click [Tạo tài khoản] button Step 3: Register with valid user name, password and email Step 4: Click [Đăng ký] button | 1. Display message "Vui lòng điền đầy đủ thông tin". | 1. Display message "Vui lòng điền đầy đủ thông tin". | Pass | 10 - Apr - 2021 | Loc | Pass | 13 - Apr - 2021 | Loc

## Report
Test Report
Project Name | English Review System |  | Creator |  | Phuong, Dau Tuan
Project Code | ER |  | Reviewer/Approver
Document Code |  |  | Date |  | 13/04/2021
Notes
No | Module Name | Pass | Fail | Not Run | N/A | Number of test cases
1 | [Server/Backend] Login for Learner | 3 | 0 | 0 | 0 | 3
2 | [Server/Backend] Logout for Learner | 1 | 0 | 0 | 0 | 1
3 | [Server/Backend] Register for Learner | 3 | 0 | 0 | 0 | 3
4 | [Server/Backend] Create an API to send lesson list data to the client | 2 | 0 | 0 | 0 | 2
5 | [Server/Backend] Create an API to send lesson content data to the server | 3 | 0 | 0 | 0 | 3
6 | [Server/Backend] Create an API to send practice content data to the client | 3 | 0 | 0 | 0 | 3
7 | [Server/Backend] Create an API to send practice according to lesson data to the client | 1 | 0 | 0 | 0 | 1
8 | [Frontend] UI for the Login page (Admin) | 5 | 0 | 0 | 0 | 5
9 | [Frontend] UI for the Login screen (Learner) | 6 | 0 | 0 | 0 | 6
10 | [Frontend] UI for the Register screen (Learner) | 7 | 0 | 0 | 0 | 7
11 | [Frontend] UI for the learner profile (Learner) | 5 | 2 | 3 | 0 | 10
12 | [Frontend] UI for the lesson page (Learner) | 23 | 0 | 0 | 0 | 23
13 | [Frontend] UI for the practice page (Learner) | 17 | 0 | 0 | 0 | 17
Total |  | 79 | 2 | 3 | 0 | 84
| Test coverage |  | 100 | %
| Test successful coverage |  | 94.0476 | %

## Bug report
Bug report of "English review system"
Project Name: | English review system |  | Date: | 2021-05-31
Testing Module | Bug Description | Steps to Reproduce |  | Expected Result | Actual result | Severity | Priority | Assigned To | Status | Links
GUI Testing
[Frontend] UI profile app | [email] button |  |  | Alignment=center, under[username]textbox |  | Critical | 1 |  | Not run
type="button"
[Frontend] UI profile app | [Đổi mật khẩu]button |  |  | Alignment=center, under[email] button type="button" |  | Critical | 1 |  | Not run
[Frontend] UI profile app | [Avatar]button |  |  | Alignment=center type="button" |  | Critical | 1 |  | Not run
[Frontend] UI lesson | Don't display score of the lesson | 1. Successful logining in Home page 2. Click[Bắt đầu học] button 3. Click [Topic] button 4. Click [Lesson] button 5. Click [Làm bài tập] button 6. Selcect all answer 7. Click[Nộp bài]button |  | 1. Display score of the lesson |  | Critical | 1 |  | Fail
[Frontend] UI Practice | Don't display score of the practice | 1. Successful logining in Home page 2. Click[Luyện tập] button 3. Click [Practice] button 4. Selcect all answer 5. Click[Nộp bài]button |  | 1. Display score of the practice |  | Critical | 1 |  | Fail