## Main
Scrum Project |  |  | Product Status
Sponsor
Product
Active versions
Product Owner
Team |  |  | Project Champion
Scrum Master |  |  | Other Stakeholders
Developers
Projects | [5 empty] | Sprint Plan |  | Project #1
Id | Description | Start | End | Status | Remarks | Sprint | Start | End | Status | Story Points (Committed) | Story Points (Delivered) | Remarks
1 | Initial release | 2019-01-07 | 2019-03-15 | In Progress |  | Spr. 1.1 | 2019-01-07 | 2019-01-18 | Complete | 3 | 3
[6 empty] | Spr. 1.2 | 2019-01-21 | 2019-02-01 | Complete | 25 | 23
[6 empty] | Spr. 1.3 | 2019-02-04 | 2019-02-15 | Complete | 20 | 18
[6 empty] | Spr. 1.4 | 2019-02-18 | 2019-03-01 | Complete | 25 | 27
[6 empty] | Spr. 1.5 | 2019-03-04 | 2019-03-15 | In Progress | 20
Formulas:
Project #1 = [Start]+11
Start = [Project #1, row above]+3

## Backlog
Backlog
Id | Epics | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint Id | Story Points (Est.) | Effort (Actual) | Owner | Status | Remarks
PB01 | Register | User | Create an account | I can shop online | - Phone # in US format, contains no alpha characters, minimum 10 digits - First name, Last name and email address required - Email specified in standard format - Email must have special character and >=8 |  | 1

## Sprint Task
Sprint Task
<- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Status | Story Points (Est.) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
1.1 | 221 | Design UI Mock Up |  |  | 3 | 3 | 0 | 1 |  | 1 | [6 empty] | 1
1.1 | 224 | Write online help test |  |  | 1 | 1 | 0 | 1
1.2 | 225 | Develop CSS/HTML |  |  | 10 | 8 | 2 | 1 | 2 | 1 | 1 | 1 |  |  | 1 |  | 1
1.2 | 229 | Develop validation criteria |  |  | 2 | 2 | 0 |  |  | 1 |  | 1
1.2 | 251 | Create database tables |  |  | 8 | 8 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2
1.2 | 253 | Code test fixtures |  |  | 5 | 0 | 5 | [5 empty] | 2 | 2 | 1
1.3 | 256 | Code & test |  |  | 20 | 18 | 2 | 3 | 2 | 1 | 2 | 2 | 2 | 2 | 1 | 2 | 1
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
|  |  |  | Total | 49 | 40 | 9 | 7 | 5 | 5 | 4 | 5 | 5 | 6 | 3 | 2 | 3
|  |  |  | Burn down |  |  |  | 42 | 37 | 32 | 28 | 23 | 18 | 12 | 9 | 7 | 4
|  |  |  | Burn up |  |  |  | 7 | 12 | 17 | 21 | 26 | 31 | 37 | 40 | 42 | 45

## Impediment
Impediments |  | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On | Remarks
Id | Description

## Retrospective
Retrospective Log |  |  |  | Start Doing | Stop Doing | Remarks
Sprint # | Date | Owner | Continue Doing

## Summary
Reports & Dashboards
Sprint Velocity
Burn down Chart | Burn up Chart

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms