## Sprint I
Sprint |  | 1 |  | SMART DASHBOARD APPLICATION
C1SE-06 Team
# | Hours available per Sprint | Member Name n |  | Comments/Notes
1 | 86 | Pham Van Tin |  | Start Date: 01.Sep.2017 | Start date | 2020-08-12
2 | 110 | Ky Huu Dong |  | End Date: 01.Otc. 2017 | End date | 2020-09-10
3 | 82 | Tran Thi Thanh Kieu
4 | 98 | Vo Van Hoa
SUM | 376 |  |  | Remanning hours |  | 0 | [38 empty] | x
How to use this: NEW SPRINT 1) Make a copy of this sheet, change X in cell D1 to sprint number. 2) Each team member estimates the number of hours they have to work in the sprint. ENTERING A NEW TASK 1) For the sprint, select a user story from the product backlog (based on input from Product Owner). 2) Break down the user story into tasks of around 0 to 8 hours. 3) For each task, enter the backlog ID in column B. a description of the task, the originator and responsible team members. 4) Finally, and most Important, enter the initial estimate in hours in column H. UPDATING Every day you should re-estimate the tasks entering the new estimate on the next day. This means you could end up with more hours on a task the next day even if you spent time on it in the current day. What is important is to know how much work is left to do. Not how much work was done. | [43 empty] | x
[9 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
No. | BACKLOG ID | Task Description (User Story/Use Case Broken Down) |  | Originator | Responsible | Status(Not Started In Progress Completed) | Inital Est. | Comp. | Day 30 12/08/2020 | Day 29 13/08/2020 | Day 28 14/08/2020 | Day 27 15/08/2020 | Day 26 16/08/2020 | Day 25 17/08/2020 | Day 24 18/08/2020 | Day 23 19/08/2020 | Day 22 20/08/2020 | Day 21 21/08/2020 | Day 20 22/08/2020 | Day 19 23/08/2020 | Day 18 24/08/2020 | Day 17 25/08/2020 | Day 16 26/08/2020 | Day 15 27/08/2020 | Day 14 28/08/2020 | Day 13 29/08/2020 | Day 12 30/08/2020 | Day 11 31/08/2020 | Day 10 01/09/2020 | Day 9 02/09/2020 | Day 8 03/09/2020 | Day 7 04/09/2020 | Day 6 05/09/2020 | Day 5 06/09/2020 | Day 4 07/09/2020 | Day 3 08/09/2020 | Day 2 09/09/2020 | Day 1 10/09/2020 | Hoa | Tin | Dong | Kieu
[7 empty] | 376 | 0 | 374 | 350 | 333 | 318 | 315 | 307 | 302 | 297 | 292 | 284 | 273 | 260 | 246 | 226 | 209 | 192 | 179 | 161 | 150 | 137 | 126 | 120 | 108 | 94 | 83 | 68 | 47 | 28 | 17 | 0
1 | Sprint Detail Plan |  |  |  | All member | Completed | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x | x | x | x | 1
2 | Sprint Backlog |  |  |  | All member | Completed | 4 | 0 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | x | x | x | x | 1
3 | Pre-sprint:fan xxzt | Planning meeting |  |  | All member | Completed | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x | x | x | x | 1
4 |  | Proposal Document |  |  | All member | Completed | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x | x | x | x | 1
5 |  | Project Plan Document |  |  | All member | Completed | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x | x | x | x | 1
6 |  | Product Backlog Document |  |  | All member | Completed | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x | x | x | x | 1
7 |  | Design Wireframe UI |  |  | All member | Completed | 8 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x | x | x | x | 2
8 | Data Modeling | Designing the Dimensional Database |  |  | Dong | Completed | 12 | 0 | 12 | 10 | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | x |  | 12
9 |  | Designing Staging Areas |  |  | Dong | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 10 | 10 | 8 | 6 | 6 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | x |  | 12
10 |  | Designing the Fact Tables |  |  | Dong | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 8 | 8 | 8 | 6 | 6 | 4 | 4 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 |  |  | x |  | 12
11 |  | Define domain for tables |  |  | Dong | Completed | 14 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 9 | 9 | 8 | 8 | 6 | 6 | 6 | 4 | 2 | 2 | 0 |  |  | x |  | 14
12 |  | Designing the Dimensional Data Store |  |  | Hoa | Completed | 12 | 0 | 12 | 8 | 8 | 6 | 6 | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 12
13 |  | Source System Mapping |  |  | Hoa | Completed | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 6 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 10
14 |  | Designing the Normalized Data Store |  |  | Hoa | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 8 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 12
15 | Physical Database Design | Configuring Databases |  |  | Hoa | Completed | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 8 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 10
16 |  | Creating Database Structure |  |  | Hoa | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 12
17 |  | Creating the Normalized Data Store |  |  | Hoa | Completed | 14 | 0 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 10 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 14
18 |  | Summary Tables |  |  | Hoa | Completed | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 10
19 |  | Partitioning |  |  | Hoa | Completed | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 10
20 | Set up database | Create database tables queries |  |  | Dong | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | x |  | 12
21 |  | Run database queries |  |  | Dong | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | x |  | 8
22 |  | Standardized CSV file data |  |  | Dong | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | x |  | 12
23 |  | Set up library Python for data processes |  |  | Dong | Completed | 20 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 15 | 10 | 5 | 0 | 0 | 0 |  |  | x |  | 20
24 | Design | Prototype |  |  | Kieu | Completed | 6 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 6
25 |  | Homepage UI |  |  | Tin | Completed | 12 | 0 | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 12
26 |  | Dashboard UI |  |  | Tin | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 12
27 | Build UI | Implement basic components | Conference Detail API |  | Tin, Kieu | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  | x | 6
28 |  | InfoSection component | Conferences List & Switch Conference API |  | Kieu | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 8
29 |  | Navbar in Homepage UI |  |  | Tin | Completed | 6 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 6
30 |  | Footer UI |  |  | Tin | Completed | 6 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 6
31 |  | Homepage UI |  |  | Kieu | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 8
32 |  | About page UI |  |  | Kieu | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 8
33 |  | Contact page UI |  |  | Kieu | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 |  |  |  | x | 8
34 |  | Navbar in Dashboard GUI |  |  | Tin | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 |  | x |  |  | 8
35 |  | Toolbar GUI |  |  | Tin | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 |  | x |  |  | 8
36 |  | Mashup Content GUI |  |  | Tin | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 |  | x |  |  | 8
37 |  | Output log UI |  |  | Tin | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 |  | x |  |  | 8
38 |  | Deploy to Firebase |  |  | Tin | Completed | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 |  | x |  |  | 2
39 |  | Add custom domain |  |  | Tin | Completed | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 |  | x |  |  | 2
40 | Testing | InfoSection test |  |  | Kieu | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 8
41 |  | Navbar test |  |  | Kieu | Completed | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 |  |  |  | x | 2
42 |  | Footer test |  |  | Kieu | Completed | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 2
43 |  | Homepage test |  |  | Kieu | Completed | 6 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 6
44 |  | About page test |  |  | Kieu | Completed | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 |  |  |  | x | 4
45 |  | Contact page test |  |  | Kieu | Completed | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 |  |  |  | x | 4
46 |  | Toolbar test |  |  | Kieu | Completed | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 |  |  |  | x | 4
[5 empty] | Working hours per day |  |  | Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
[5 empty] | 12.95 |  |  | EST | 376 | 363.05 | 350.1 | 337.15 | 324.2 | 311.25 | 298.3 | 285.35 | 272.4 | 259.45 | 246.5 | 233.55 | 220.6 | 207.65 | 194.7 | 181.75 | 168.8 | 155.85 | 142.9 | 129.95 | 117 | 104.05 | 91.1 | 78.15 | 65.2 | 52.25 | 39.3 | 26.35 | 13.4 | 0.45
[8 empty] | Actual | 374 | 350 | 333 | 318 | 315 | 307 | 302 | 297 | 292 | 284 | 273 | 260 | 246 | 226 | 209 | 192 | 179 | 161 | 150 | 137 | 126 | 120 | 108 | 94 | 83 | 68 | 47 | 28 | 17 | 0

## Sprint II
Sprint |  | 2 | Smart Dashboard Application
C1SE-06 Team
# | Hours available per Sprint | Member Name | Comments/Notes
1 | 95 | Pham Van Tin | Start Date: 01.Sep.2017 | Start date | 2020-09-11
2 | 104 | Ky Huu Dong | End Date: 01.Otc. 2017 | End date | 2020-10-10
3 | 33 | Tran Thi Thanh Kieu
4 | 101 | Vo Van Hoa
SUM | 333 |  | Remanning hours |  | -23 | [38 empty] | x
How to use this: NEW SPRINT 1) Make a copy of this sheet, change X in cell D1 to sprint number. 2) Each team member estimates the number of hours they have to work in the sprint. ENTERING A NEW TASK 1) For the sprint, select a user story from the product backlog (based on input from Product Owner). 2) Break down the user story into tasks of around 0 to 8 hours. 3) For each task, enter the backlog ID in column B. a description of the task, the originator and responsible team members. 4) Finally, and most Important, enter the initial estimate in hours in column H. UPDATING Every day you should re-estimate the tasks entering the new estimate on the next day. This means you could end up with more hours on a task the next day even if you spent time on it in the current day. What is important is to know how much work is left to do. Not how much work was done. | [42 empty] | x
[8 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
No. | BACKLOG ID | Task Description (User Story/Use Case Broken Down) | Originator | Responsible | Status(Not Started In Progress Completed) | Inital Est. | Comp. | Day 30 11/09/2020 | Day 29 12/09/2020 | Day 28 13/09/2020 | Day 27 14/09/2020 | Day 26 15/09/2020 | Day 25 16/09/2020 | Day 24 17/09/2020 | Day 23 18/09/2020 | Day 22 19/09/2020 | Day 21 20/09/2020 | Day 20 21/09/2020 | Day 19 22/09/2020 | Day 18 23/09/2020 | Day 17 24/09/2020 | Day 16 25/09/2020 | Day 15 26/09/2020 | Day 14 27/09/2020 | Day 13 28/09/2020 | Day 12 29/09/2020 | Day 11 30/09/2020 | Day 10 01/10/2020 | Day 9 02/10/2020 | Day 8 03/10/2020 | Day 7 04/10/2020 | Day 6 05/10/2020 | Day 5 06/10/2020 | Day 4 07/10/2020 | Day 3 08/10/2020 | Day 2 09/10/2020 | Day 1 10/10/2020 | Hoa | Tin | Dong | Kieu
[6 empty] | 356 | 23 | 356 | 343 | 330 | 319 | 313 | 306 | 299 | 286 | 277 | 268 | 252 | 237 | 225 | 212 | 196 | 187 | 173 | 163 | 151 | 137 | 124 | 114 | 110 | 98 | 89 | 72 | 54 | 39 | 31 | 23
1 | Sprint Detail Plan |  |  | All member | Completed | 4 | 0 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | x | x | x | x | 1
2 | Sprint Backlog |  |  | All member | Completed | 4 | 0 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | x | x | x | x | 1
3 | Pre-sprint | Planning meeting |  | Kieu | Completed | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 4
4 |  | Sprint Retrospective |  | All member | Completed | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x | x | x | x | 1
5 | Finding Data | Using Scrapy to scrawl data |  | Dong | Completed | 16 | 0 | 16 | 16 | 14 | 14 | 14 | 14 | 14 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | x |  | 16
6 |  | Source System Mapping |  | Dong | Completed | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | x |  | 10
7 |  | Standardized data founded |  | Dong | Completed | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | x |  | 10
8 | Data processing | Extract data to Staging Areas |  | Dong | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | x |  | 12
9 |  | Transform Data to Staging Areas |  | Dong | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 10 | 8 | 8 | 6 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | x |  | 12
10 |  | Load data to Staging Areas |  | Dong | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 3 | 0 | 0 | 0 | 0 |  |  | x |  | 12
11 |  | Summary Tables |  | Dong | Completed | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  |  | x |  | 1
12 |  | Extract data from Staging Area to Facts table |  | Dong | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 10 | 8 | 6 | 4 | 2 | 2 | 0 | 0 |  |  | x |  | 12
13 |  | Transform Data to Staging Areas to Facts table |  | Dong | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 4 | 4 | 2 | 2 | 0 |  |  | x |  | 8
14 |  | Load data to Staging Areas to Facts table |  | Dong | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 5 | 3 | 0 |  |  | x |  | 8
15 | Data Warehouse Designing | Validating extract process |  | Hoa | Completed | 12 | 0 | 12 | 12 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 12
16 |  | Defining transform requirements |  | Hoa | Completed | 15 | 0 | 15 | 13 | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 15
17 |  | Defining DW design pattern |  | Hoa | Completed | 15 | 0 | 15 | 15 | 15 | 15 | 15 | 13 | 10 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 15
18 |  | Defining DW schemas |  | Hoa | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 12
19 |  | Designing fact tables & dimensional tables |  | Hoa | Completed | 16 | 0 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 12 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 16
20 | ETL Process Validating | Validating transform process |  | Hoa | Completed | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 10
21 |  | Validating load process |  | Hoa | Completed | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 0 | 0 | 0 | x |  |  |  | 10
22 |  | Validating DW Structure |  | Hoa | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | x |  |  |  | 8
23 | Dashboard UI | Modal UI |  | Tin | Completed | 6 | 0 | 6 | 5 | 5 | 5 | 5 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 6
24 |  | User Guide GUI |  | Tin | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  | x |  |  | 0
25 |  | Drag item from Toolbar and drop to Mashup Content |  | Tin | Completed | 6 | 0 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 6
26 |  | Viz Node in Table Tree View |  | Tin | In Progress | 6 | 1 | 6 | 6 | 6 | 6 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | x |  |  | 5
27 |  | Draw connector to link 2 node |  | Tin | Completed | 12 | 0 | 12 | 12 | 12 | 10 | 8 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 12
28 |  | Initial Pie Chart |  | Tin | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 8
29 |  | Initial Maps with highchart |  | Tin | Completed | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 10
30 |  | Highlight province in Maps |  | Tin | In Progress | 16 | 0 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 14 | 12 | 10 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 16
31 |  | Viz Humidity in tree view |  | Tin | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 8
32 |  | Viz Humidity filter by city in tree view |  | Tin | Completed | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 10
33 |  | Viz Humidity filter by city in Line Chart |  | Tin | In Progress | 12 | 2 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 8 | 6 | 4 | 2 | 2 | 2 | 2 |  | x |  |  | 10
34 |  | Deploy to Firebase |  | Tin | Completed | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  | x |  |  | 1
35 | Testing | Modal test |  | Kieu | Completed | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 4
36 |  | User Guide test |  | Kieu | In Progress | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  |  | x | 0
37 |  | connector between 2 node test |  | Kieu | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 4 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 8
38 |  | drag & drop node test |  | Kieu | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 |  |  |  | x | 8
39 |  | Check data in Line Chart on humiduty filter by city |  | Kieu | In Progress | 12 | 6 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 6 | 6 | 6 |  |  |  | x | 6
|  |  |  | Working hours per day |  |  | Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
|  |  |  | 12.27 |  |  | EST | 356 | 343.73 | 331.46 | 319.19 | 306.92 | 294.65 | 282.38 | 270.11 | 257.84 | 245.57 | 233.3 | 221.03 | 208.76 | 196.49 | 184.22 | 171.95 | 159.68 | 147.41 | 135.14 | 122.87 | 110.6 | 98.33 | 86.06 | 73.79 | 61.52 | 49.25 | 36.98 | 24.71 | 12.44 | 0.17
[7 empty] | Actual | 356 | 343 | 330 | 319 | 313 | 306 | 299 | 286 | 277 | 268 | 252 | 237 | 225 | 212 | 196 | 187 | 173 | 163 | 151 | 137 | 124 | 114 | 110 | 98 | 89 | 72 | 54 | 39 | 31 | 23

## Sprint III
Sprint |  | 3 | Smart Dashboard Application
C1SE-06 Team
# | Hours available per Sprint | Member Name | Comments/Notes
1 | 105 | Pham Van Tin | Start Date: 01.Sep.2017 | Start date | 2020-10-11
2 | 69 | Ky Huu Dong | End Date: 01.Otc. 2017 | End date | 2020-11-09
3 | 29 | Tran Thi Thanh Kieu
4 | 147 | Vo Van Hoa
SUM | 350 |  | Remanning hours |  | -37 | [38 empty] | x
How to use this: NEW SPRINT 1) Make a copy of this sheet, change X in cell D1 to sprint number. 2) Each team member estimates the number of hours they have to work in the sprint. ENTERING A NEW TASK 1) For the sprint, select a user story from the product backlog (based on input from Product Owner). 2) Break down the user story into tasks of around 0 to 8 hours. 3) For each task, enter the backlog ID in column B. a description of the task, the originator and responsible team members. 4) Finally, and most Important, enter the initial estimate in hours in column H. UPDATING Every day you should re-estimate the tasks entering the new estimate on the next day. This means you could end up with more hours on a task the next day even if you spent time on it in the current day. What is important is to know how much work is left to do. Not how much work was done. | [42 empty] | x
[8 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
No. | BACKLOG ID | Task Description (User Story/Use Case Broken Down) | Originator | Responsible | Status(Not Started In Progress Completed) | Inital Est. | Comp. | Day 30 11/10/2020 | Day 29 12/10/2020 | Day 28 13/10/2020 | Day 27 14/10/2020 | Day 26 15/10/2020 | Day 25 16/10/2020 | Day 24 17/10/2020 | Day 23 18/10/2020 | Day 22 19/10/2020 | Day 21 20/10/2020 | Day 20 21/10/2020 | Day 19 22/10/2020 | Day 18 23/10/2020 | Day 17 24/10/2020 | Day 16 25/10/2020 | Day 15 26/10/2020 | Day 14 27/10/2020 | Day 13 28/10/2020 | Day 12 29/10/2020 | Day 11 30/10/2020 | Day 10 31/10/2020 | Day 9 01/11/2020 | Day 8 02/11/2020 | Day 7 03/11/2020 | Day 6 04/11/2020 | Day 5 05/11/2020 | Day 4 06/11/2020 | Day 3 07/11/2020 | Day 2 08/11/2020 | Day 1 09/11/2020 | Hoa | Tin | Dong | Kieu
[6 empty] | 387 | 37 | 383 | 367 | 355 | 346 | 340 | 335 | 323 | 310 | 296 | 277 | 264 | 249 | 238 | 214 | 208 | 201 | 184 | 171 | 151 | 133 | 114 | 108 | 95 | 87 | 72 | 68 | 58 | 54 | 46 | 41
1 | Sprint Detail Plan |  |  | All members | Completed | 4 | 0 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | x | x | x | x | 1
2 | Sprint Backlog |  |  | Kieu | Completed | 4 | 0 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  |  | x | 4
3 | Pre-sprint | Planning meeting |  | Kieu | Completed | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 4
4 |  | Sprint Retrospective |  | All members | Completed | 8 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x | x | x | x | 2
5 | Expanding database | Add fact to database |  | Dong | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 6 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | x |  | 12
6 |  | Add dimention to database |  | Dong | Completed | 14 | 0 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 10 | 8 | 8 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | x |  | 14
7 |  | Add data to database |  | Dong | Completed | 20 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 18 | 16 | 14 | 12 | 10 | 8 | 6 | 4 | 4 | 4 | 0 | 0 | 0 | 0 |  |  | x |  | 20
8 | Crawl data | Use scrapy to crawl data |  | Dong | Completed | 20 | 8 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 18 | 16 | 14 | 12 | 10 | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  |  | x |  | 12
9 |  | Arrange data |  | Dong | Completed | 12 | 8 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 8 | 8 | 8 | 8 | 8 |  |  | x |  | 4
10 |  | Normalized and Standardized data |  | Dong | Completed | 12 | 8 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 8 | 8 | 8 | 8 | 8 |  |  | x |  | 4
11 | RDF Data Cubes Designing | Design Common RDF Data Cube Structure |  | Hoa | Completed | 12 | 0 | 12 | 10 | 5 | 5 | 5 | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 12
12 |  | Design Climate Data Cube Structure |  | Hoa | Completed | 12 | 0 | 12 | 12 | 12 | 9 | 6 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 12
13 |  | Design Industrial Data Cubes Structure |  | Hoa | Completed | 12 | 0 | 12 | 12 | 12 | 10 | 10 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 12
14 | Setting up DW to RDF Process Tool & Environment | Setting up Google Open Refine |  | Hoa | Completed | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 10
15 |  | Connecting DW to Google Open Refine |  | Hoa | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 8
16 |  | Create DW2RDF project on Open Refine |  | Hoa | Completed | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 10
17 | Implementing DW2RDF Process | Implementing RDF Data Cubes Structure |  | Hoa | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 12
18 |  | Varying & Extract DW2RDF Skeleton |  | Hoa | Completed | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 10
19 |  | Climate Dataset DW2RDF Processing |  | Hoa | Completed | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 10
20 |  | Extracting Climate Data Cubes as Turtle |  | Hoa | Completed | 5 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 5
21 |  | Industrial Dataset DW2RDF Processing |  | Hoa | Completed | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 10
22 |  | Extracting Industrial Data Cubes as Turtle |  | Hoa | Completed | 5 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 5
23 | Setting up RDF Data Cubes Storing & SPARQL Endpoint | Setting up GraphDB |  | Hoa | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 12
24 |  | Upload RDF Data Cubes onto GraphDB |  | Hoa | Completed | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | x |  |  |  | 4
25 |  | Setting up GraphDB Endpoint |  | Hoa | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 8 | 3 | 3 | 3 | 3 | 3 | 0 | x |  |  |  | 12
26 | Dashboard UI | Viz Humidity filter by city in Column Chart |  | Tin | Completed | 12 | 0 | 12 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 12
27 |  | Viz Industry in tree view |  | Tin | Completed | 8 | 0 | 8 | 8 | 8 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 8
28 |  | Viz Industry filter by year in tree view |  | Tin | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 8
29 |  | Viz Industry filter by city in tree view |  | Tin | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 8
30 |  | Viz Industry in Maps |  | Tin | Completed | 24 | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 20 | 18 | 15 | 12 | 10 | 6 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 24
31 |  | Viz Temperature in tree view |  | Tin | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 8
32 |  | Viz Temperature filter by city in tree view |  | Tin | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 8
33 |  | Merge widget Temperature & industry |  | Tin | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 4 |  | x |  |  | 8
34 |  | Highligh industry data in maps of each province |  | Tin | Completed | 12 | 4 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 6 | 6 | 6 | 6 | 6 | 4 | 4 |  | x |  |  | 8
35 |  | Track point of each province temperature data in maps |  | Tin | Completed | 12 | 2 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 6 | 4 | 2 | 2 |  | x |  |  | 10
36 |  | Deploy to Firebase |  | Tin | Completed | 1 | 1 | [31 empty] | x |  |  | 0 | bar: 0 to 29
37 | Testing | Check filter by year industry |  | Kieu | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 8
38 |  | Check filter by city industry |  | Kieu | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 8
39 |  | Check data industry in Maps |  | Kieu | Completed | 8 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 6 |  |  |  | x | 2
|  |  |  | Working hours per day |  |  | Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
|  |  |  | 13.33 |  |  | EST | 387 | 373.67 | 360.34 | 347.01 | 333.68 | 320.35 | 307.02 | 293.69 | 280.36 | 267.03 | 253.7 | 240.37 | 227.04 | 213.71 | 200.38 | 187.05 | 173.72 | 160.39 | 147.06 | 133.73 | 120.4 | 107.07 | 93.74 | 80.41 | 67.08 | 53.75 | 40.42 | 27.09 | 13.76 | 0.43
[7 empty] | Actual | 383 | 367 | 355 | 346 | 340 | 335 | 323 | 310 | 296 | 277 | 264 | 249 | 238 | 214 | 208 | 201 | 184 | 171 | 151 | 133 | 114 | 108 | 95 | 87 | 72 | 68 | 58 | 54 | 46 | 41

## Sprint IV
Sprint |  | 4 | Smart Dashboard Application
C1SE-06 Team
# | Hours available per Sprint | Member Name | Comments/Notes
1 | 132 | Pham Van Tin | Start Date: 01.Sep.2017 | Start date | 2020-11-10
2 | 56 | Ky Huu Dong | End Date: 01.Otc. 2017 | End date | 2020-12-09
3 | 88 | Tran Thi Thanh Kieu
4 | 167 | Vo Van Hoa
SUM | 443 |  | Remanning hours |  | -71 | [38 empty] | x
How to use this: NEW SPRINT 1) Make a copy of this sheet, change X in cell D1 to sprint number. 2) Each team member estimates the number of hours they have to work in the sprint. ENTERING A NEW TASK 1) For the sprint, select a user story from the product backlog (based on input from Product Owner). 2) Break down the user story into tasks of around 0 to 8 hours. 3) For each task, enter the backlog ID in column B. a description of the task, the originator and responsible team members. 4) Finally, and most Important, enter the initial estimate in hours in column H. UPDATING Every day you should re-estimate the tasks entering the new estimate on the next day. This means you could end up with more hours on a task the next day even if you spent time on it in the current day. What is important is to know how much work is left to do. Not how much work was done. | [42 empty] | x
[8 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
No. | BACKLOG ID | Task Description (User Story/Use Case Broken Down) | Originator | Responsible | Status(Not Started In Progress Completed) | Inital Est. | Comp. | Day 30 10/11/2020 | Day 29 11/11/2020 | Day 28 12/11/2020 | Day 27 13/11/2020 | Day 26 14/11/2020 | Day 25 15/11/2020 | Day 24 16/11/2020 | Day 23 17/11/2020 | Day 22 18/11/2020 | Day 21 19/11/2020 | Day 20 20/11/2020 | Day 19 21/11/2020 | Day 18 22/11/2020 | Day 17 23/11/2020 | Day 16 24/11/2020 | Day 15 25/11/2020 | Day 14 26/11/2020 | Day 13 27/11/2020 | Day 12 28/11/2020 | Day 11 29/11/2020 | Day 10 30/11/2020 | Day 9 01/12/2020 | Day 8 02/12/2020 | Day 7 03/12/2020 | Day 6 04/12/2020 | Day 5 05/12/2020 | Day 4 06/12/2020 | Day 3 07/12/2020 | Day 2 08/12/2020 | Day 1 09/12/2020 | Hoa | Tin | Dong | Kieu
[6 empty] | 514 | 71 | 514 | 493 | 468 | 440 | 420 | 414 | 412 | 399 | 385 | 377 | 375 | 372 | 356 | 341 | 330 | 322 | 301 | 289 | 279 | 256 | 243 | 239 | 210 | 191 | 172 | 157 | 132 | 113 | 101 | 71
1 | Sprint Detail Plan |  |  | All members | Completed | 4 | 0 | 4 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x | x | x | x | 1
2 | Sprint Backlog |  |  | Kieu | Completed | 4 | 0 | 4 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 4
3 | Pre-sprint | Planning meeting |  | Kieu | Completed | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 4
4 |  | Sprint Retrospective |  | All members | Completed | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x | x | x | x | 1
5 | Documents | Reworking Proposal |  | Kieu | Completed | 4 | 0 | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 4
6 |  | Reworking Project Plan |  | Kieu | Completed | 4 | 0 | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 4
7 |  | Architecture Document |  | All members | Completed | 24 | 0 | 24 | 20 | 16 | 12 | 6 | 4 | 4 | 4 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | x | x | x | x | 6
8 |  | Interface Desgin |  | Tin, Kieu | Completed | 12 | 0 | 12 | 12 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 |  | x |  | x | 6
9 |  | Database Design |  | Hoa, Dong | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 6 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | x |  | x |  | 6
10 |  | Test Plan |  | All members | Completed | 4 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x | x | x | x | 1
11 |  | Test Case |  | All members | Completed | 8 | 0 | 8 | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | x | x | x | x | 2
12 |  | Acceptance Criteria |  | Kieu, Tin | In Progress | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 |  | x |  | x | 2
13 |  | Technologies Stack |  | All members | In Progress | 4 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x | x | x | x | 1
14 |  | Team Reflection |  | All members | In Progress | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | x | x | x | x | 1
15 |  | Team meeting document |  | Kieu | In Progress | 4 | 1 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | x | 3
16 |  | Mentor meeting document |  | Kieu | In Progress | 4 | 1 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | x | 3
17 | Enrich the data | Tools for ETL |  | Dong | In Progress | 12 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 10 |  |  | x |  | 2
18 |  | Crawl data from Mekong data |  | Dong | Not Started | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  |  | x |  | 0
19 |  | Design queries for new tables |  | Dong | Not Started | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 |  |  | x |  | 0
20 |  | Run queries to create data tables |  | Dong | Not Started | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  |  | x |  | 0
21 |  | Load data into Data warehouse |  | Dong | Not Started | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  |  | x |  | 0
22 | Validating | Validating queries result |  | Dong | Completed | 20 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 18 | 16 | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | x |  | 20
23 |  | Validating loading process result |  | Dong | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 |  |  | x |  | 12
24 | Validating RDF Data Cubes | Validating Climate Observations |  | Hoa | Completed | 10 | 0 | 10 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 10
25 |  | Validating Climate Dimensions & Measures |  | Hoa | Completed | 10 | 0 | 10 | 10 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 10
26 |  | Validating Industrial Observations |  | Hoa | Completed | 10 | 0 | 10 | 10 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 10
27 |  | Validating Industrial Dimensions & Measures |  | Hoa | Completed | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 10
28 | Building SPARQL-REST API | Setting up Environment |  | Hoa | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 7 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 12
29 |  | Building sample SPARQL-REST API |  | Hoa | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 6 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | x |  |  |  | 12
30 |  | Building SDA's SPARQL-REST API |  | Hoa | Completed | 35 | 0 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 20 | 15 | 12 | 8 | 4 | 0 | 0 | 0 | x |  |  |  | 35
31 | Deploying | Setting up Linux Virtual Machine |  | Hoa | Completed | 20 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 18 | 14 | 12 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | x |  |  |  | 20
32 |  | Deploying system to VPS |  | Hoa | Completed | 20 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 5 | 5 | 0 | 0 | 0 | x |  |  |  | 20
33 | Dashboard UI | Merge widget Climate & Industry |  | Tin | Completed | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 4
34 |  | Highligh industry data in maps of each province |  | Tin | Completed | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 4
35 |  | Track point of each province temperature data in maps |  | Tin | Completed | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 2
36 |  | Output log in properties |  | Tin | In Progress | 8 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | x |  |  | 5
37 |  | Output log in Widget infos |  | Tin | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 8
38 |  | Output log function |  | Tin | In Progress | 8 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | x |  |  | 6
39 |  | New button function |  | Tin | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 |  | x |  |  | 8
40 |  | User Guide button function |  | Tin | Not Started | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  | x |  |  | 0
41 |  | Viz Forest Filter By Year In Maps |  | Tin | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 8
42 |  | Viz Forest Filter By City in Column |  | Tin | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 8
43 |  | Viz Forest Filter by period of city in Column & Maps |  | Tin | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 8
44 |  | Merge widget Forest & Climate |  | Tin | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 4 | 0 | 0 | 0 | 0 |  | x |  |  | 12
45 |  | Intergrate with Cloud Server |  | Tin | Completed | 24 | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 22 | 21 | 20 | 20 | 19 | 18 | 16 | 14 | 12 | 12 | 10 | 8 | 8 | 4 | 0 | 0 | 0 | 0 |  | x |  |  | 24
46 |  | Deploy to Firebase |  | Tin | Completed | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  | x |  |  | 1
47 | Testing | Check data industry in Maps |  | Kieu | Completed | 6 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 6
48 |  | Check filter by city in Temperature |  | Kieu | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 8 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 12
49 |  | Check data in Maps when merge Climate & Industry |  | Kieu | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 8 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 12
50 |  | Check data in Maps when merge Climate & Forest |  | Kieu | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 2 | 0 |  |  |  | x | 12
51 | Presentation |  |  | All members | In Progress | 12 | 0 | 12 | 12 | 12 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | x | x | x | x | 3
52 | Print Document |  |  | Tin | In Progress | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 |  | x |  |  | 4
53 | Deployment & Release |  |  | Tin, Hoa | In Progress | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 4 | 0 | x | x |  |  | 6
|  |  |  | Working hours per day |  |  | Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
|  |  |  | 17.71 |  |  | EST | 514 | 496.29 | 478.58 | 460.87 | 443.16 | 425.45 | 407.74 | 390.03 | 372.32 | 354.61 | 336.9 | 319.19 | 301.48 | 283.77 | 266.06 | 248.35 | 230.64 | 212.93 | 195.22 | 177.51 | 159.8 | 142.09 | 124.38 | 106.67 | 88.96 | 71.25 | 53.54 | 35.83 | 18.12 | 0.41
[7 empty] | Actual | 514 | 493 | 468 | 440 | 420 | 414 | 412 | 399 | 385 | 377 | 375 | 372 | 356 | 341 | 330 | 322 | 301 | 289 | 279 | 256 | 243 | 239 | 210 | 191 | 172 | 157 | 132 | 113 | 101 | 71

## Note
There are problem with this task, like OT…
By this time this task must be done on plan
Place to input data